### Terms of Reference

### Agro-biodiversity and plant specialist

### Conservation and sustainable use of globally important agro-biodiversity

### Location: Baku, Azerbaijan

### Type of contract: IC

Starting date: 26 March, 2021

End date: 10 December, 2021

Background

The project seeks to: (i) improve the protection of viable populations of indigenous wild relatives of crops and local landraces in their natural habitats; (ii) augment the conservation of indigenous wild relatives of crops and local landraces in plant gene banks to ensure an adequate source of genetic resources for plant breeding; and (iii) increase the production, and extent of use, of local landraces in agricultural small holdings and commercial farms.

The project will be implemented in three regions - Sheki, Goranboy and Goychay. Within these three rayons, the project will further focus on selected crop wild relatives, cultivated native species and cultivated landraces of wheat, vegetable and forage crops.

The project has been structured into three complementary components.

The first component will seek to expand the state of knowledge of agro-biodiversity, enhance the conservation of this agro-biodiversity and increase the intensity and extent of use native crops in the agricultural sector in the three project regions.

The second component will seek to build the capacities of, and improve the collaboration and cooperation between, agricultural institutions and small farmers in order to improve agricultural productivity and reduce land degradation using native crops (i.e. the targeted crop species) in the three project regions.

The third component will seek to strengthen incentives that encourage the planting of, and improve access to commercial markets for agricultural products derived from, the targeted native crop species across the three regions.

Scope of work

- Establishment of a field gene bank of local varieties and organization of agro-technical care for them

- Developing a breeding plan to ensure the continuity of selection activities for the creation of new varieties adopted for the current climate change

- Organization of work with farmers in target areas

- Collection and analysis of information on the planting of local varieties across the country and target regions

- Evaluation of the productivity of cereals and fodder crops sown in field gene banks and farmers' areas and development of proposals for value added

- Support the establishment, formal registration and operational management of the seed production fields of at least one vegetable farmer in Goranboy

- Update the information of farmers engaged in seed production

- Organization of regular meetings and consultation workshops for the establishment of the supported farmers’ union on cereals

- Update the list of farmers engaged in the cultivation of local varieties in the target areas

- Preparation of a report on the productivity and quality of varieties provided to farmers under the project.

- Support the dissemination of existing practices on selected farms

- Organization of seminars and field days of created varieties in scientific research institutes

- Assist in the development of the project’s annual report

- Other tasks requested by UNDP.

Deliverables

| N | Deliverable | Timeline |
| --- | --- | --- |
| 1 | Developing a breeding plan to ensure the continuity of selection activities for the creation of new varieties adopted for the current climate change | March-April, 2021 |
| 2 | Collection and analysis of information on the planting of local varieties across the country and target regions | March-April, 2021 |
| 3 | Evaluation of the productivity of cereals and fodder crops sown in field gene banks and farmers' areas and development of proposals for value added | May-June, 2021 |
| 4 | Update the information of farmers engaged in seed production | June-September, 2021 |
| 5 | Support the establishment, formal registration and operational management of the seed production fields of at least one vegetable farmer in Goranboy | June-September, 2021 |
| 6 | Update the list of farmers engaged in the cultivation of local varieties in the target areas | April-December, 2021 |
| 7 | Preparation of a report on the productivity and quality of varieties provided to farmers under the project. | March-December, 2021 |
| 8 | Support the dissemination of existing practices on selected farms | April-December, 2021 |
| 9 | Assist in the development of the project’s annual report | March-December, 2021 |
| 10 | Establishment of a field gene bank of local varieties and organization of agro-technical care for them | March-December, 2021 |
| 11 | Organization of work with farmers in target areas | March-December, 2021 |
| 12 | Organization of regular meetings and consultation workshops for the establishment of the supported farmers union on cereals | March-December, 2021 |
| 13 | Organization of seminars and field days of created varieties in scientific research institutes | March-December, 2021 |

Monitoring: Agro-biodiversity and plant specialist will be an experienced national expert to prepare all documents on landraces and new breeding varieties on vegetable celeal and fruit plants. He/She will work with Project Agricultural Scientist and report to National Project Manager (NPM). The incumbent is expected to exercise full compliance with UNDP programming, financial, procurement and administrative rules, regulations, policies and strategies. During the contract period the working days: 180 days.

Qualifications and Competencies

- PHD in Agronomy or Breeding;

- At least 10 years’ experience on breeding and planting;

- At least 7 years’ experience on field genbank operation;

- Strong drafting, presentation and reporting skills;

- Previous experience with UN Agencies

Technical skills

- A working knowledge of spoken and written of Azeri and English is required, including the ability to writing reports.

- Excellent computer skills, in particular mastery of all applications of the MS Office package;

Please note that for any additional information or clarification interview can be conducted with shortlisted candidates. The language of interview: English.

Terms of Payment:

Payment will be done in four instalments and based on completion of deliverables.

- 1st instalment – 20% payment- deliverable 1 (April, 2021)

- 2nd instalment – 25% - deliverables 2, 3 (June, 2021)

- 3rd instalment – 25% - deliverable 4, 5 (September, 2021)

- 4th instalment – 30% - deliverables 6, 7, 8, 9, 10, 11, 12, 13 (December, 2021)

No international travel is expected. In case of any urgent need for an international travel, expenses will be covered by project. Total no of days in the field out of Baku in rayons: 80 days (local travel). Daily allowance for internal travel is USD 96 per day.

Financial proposal should be done as a lump sum in consideration of supposed travels to the Project area. The breakdown is necessary.