Date:  May 19, 2023

REQUEST FOR QUOTATION

RFQ Nº UNFPA/AZE/RFQ/23/014

Dear Sir/Madam,

UNFPA hereby solicits a quotation for the following service:

To conduct advocacy campaign dedicated to International Father’s Day by promoting responsible fatherhood and stronger bonds between fathers and their children with special focus on a girl child.

This Request for Quotation is open to all legally constituted organization that can provide the requested services and have legal capacity to perform in the country, or through an authorized representative.

- About UNFPA

UNFPA, the United Nations Population Fund (UNFPA), is an international development agency that works to deliver a world where every pregnancy is wanted, every childbirth is safe and every young person’s potential is fulfilled.

UNFPA is the lead UN agency that expands the possibilities for women and young people to lead healthy sexual and reproductive lives. To read more about UNFPA, please go to: UNFPA about us

- Service Requirements/Terms of Reference (ToR)

UNFPA, the United Nations Population Fund: Delivering a world where every pregnancy is wanted, every childbirth is safe and every young person’s potential is fulfilled.

Background

UNFPA is the United Nations sexual and reproductive health agency, with the field offices present in more than 150 countries across the world. The UNFPA office in Baku is engaged in implementation of the projects and programmes in the field of gender equality, population dynamics and family planning.

UNFPA vision is for a world where all girls and boys are equally heard and valued. This is a world built on transformative change – to the dismantling of patriarchal, discriminatory gender norms and the inequalities they sustain. These norms affect both boys and girls but have a disproportionate impact on girls, preventing them from claiming their rights, exposing them to harmful practices, driving rights abuses in their homes, relationships and communities, and through embedded structural inequalities that shape their lives from childhood through adulthood.

UNFPA supports the governments around the globe to build the world free from gender-based discrimination and violence, where all women and girls fully enjoy their right to have equal opportunities, to decide their own future and empower those around them.

For more than two decades, UNFPA Azerbaijan has been on the forefront of advocacy efforts to promote gender equality and ensure equal opportunities and outcomes for women and girls including through improved legal and policy frameworks and gender-sensitive data collection, initiatives that improve women's and girls' health and expand their choices, projects to transform patriarchal and discriminatory gender stereotypes and harmful traditional practices. Among many other initiatives, UNFPA celebrates related international days to ensure wider publicity and dissemination of information related to gender equality issues. The International Fathers’ Day is one of these special occasions to promote gender equitable relations in both public and private domains, including responsible fatherhood and equal distribution of household chores for the well-balanced and healthy family. UNFPA celebrated the first ever International Father’s Day in 2022 by organizing a series of activities, including open air event, Fathers’ Camp, as well as production of a video story dedicated to responsible fathering experiences. To ensure sustainability of the action, UNFPA is planning to celebrate the International Fathers’ Day 2023 as a part of its ongoing advocacy efforts as well as in the framework of the project on “Addressing Gender-Biased Sex Selection and Related Harmful Practices in the South Caucasus: Support for Regional, National and South–South Interventions” funded by the EU and implemented by UNFPA.

Hence, UNFPA Azerbaijan is seeking the services of the local agencies/organizations for conducting the advocacy campaign dedicated to the International Father’s Day to celebrate gender equitable parenting by promoting responsible fatherhood and stronger bonds between fathers and their children with special focus on a girl child.

Purpose

The campaign is expected to engage men as agents of change for challenging the prevailing gender stereotypes. More specifically, this initiative is seeking to organize and hold a series of activities advocating for responsible fatherhood, gaining new skills in parenting, encouraging them to spend more time with their kids, with special focus on girl children, thus promoting a model of equal responsibilities and care in the family, addressing son preference and increasing the value of girls.

Responsibilities of the organizer

The agency sub-contracted for the implementation of the subject assignment is to provide full organizational and logistical support to the activities listed below and will be specifically responsible for the following:

- Initial orientation with UNFPA Azerbaijan Country Office (CO) to discuss and agree on the intervention strategies proposed. To liaise closely with the UNFPA CO in Azerbaijan at each stage of the project implementation;

- To develop a context specific outline of the proposed intervention strategies of the campaign.

- To use the most creative and outreach techniques to organize the campaign – subject to the approval of UNFPA Azerbaijan CO;

- To solicit necessary authorization by local authorities for the venue/location identified for the purposes of the campaign;

- To ensure the produced content is promoting gender equitable parenting, the value of a girl child, and responsible fatherhood;

- To ensure that all technical issues, including but not limited to official authorization are well addressed prior to the campaign launch;

- To ensure extensive outreach and visibility of the campaign in traditional and social media;

- To ensure visibility and acknowledgement of UNFPA and EU throughout the campaign, in media coverage and printed materials if any;

- To ensure that the actions and messages delivered through the campaign are used only upon approval of the UNFPA Azerbaijan CO and do not compromise UNFPA mandate;

- To provide regular updates to UNFPA CO on the progress achieved alongside the comprehensive narrative and financial reports, including video and photo materials.

Deliverables:

- The campaign’s concept note followed with the detailed action plan;

- # of communication products produced (e.g. print publications, e-publications, videos/PSAs, promo materials, etc.)

- # of people reached;

- Photos and videos taken during the event/s;

- Comprehensive final narrative and financial reports.

Eligibility criteria:

- Have registration as a legal non-profit entity or public entity;

- Have proven experience of at least three years in organization and implementation of awareness raising activities/national level campaigns on various social issues, including gender equality;

- Have professional team of experts with relevant background, expertise, strong interpersonal skills;

- Experience of working within strict deadlines;

- Previous experience of working with UNFPA/UN is an asset.

Contract duration:

May-June 2023

Specific Conditions:

Ownership of the output: UNFPA

- Questions

Questions or requests for further clarifications should be submitted in writing to the contact person below:

| Name of contact person at UNFPA: | Ms. Naila Jafarova |
| --- | --- |
| Tel Nº: | +99412 4922470 |
| Fax Nº: | +99412 4922379 |
| Email address of contact person: | manafova@unfpa.org |

The deadline for submission of questions is 29.05.2023, 12:00PM, Baku time. Questions will be answered in writing and shared with all parties as soon as possible after this deadline.

- Content of quotations

Quotations should be submitted as a hard copy or in a single e-mail whenever possible, depending on file size. Quotations must contain:

- Technical proposal, in response to the requirements outlined in the service requirements / TORs.

- Price quotation, to be submitted strictly in accordance with the price quotation form.

Both parts of the quotation must be signed by the bidding organization’s relevant authority and submitted in PDF format.

- Instructions for submission

Proposals should be prepared based on the guidelines set forth in Section IV above, along with a properly filled out and signed price quotation form and technical proposal, are to be sent in hardcopy by mail in sealed and stamped envelope or by e-mail to the contact person indicated below no later than: June 01, 2023, at 12:00PM Baku time.

| Name of contact person at UNFPA: | Ms. Yegana Ismailova |
| --- | --- |
| Email address of contact person: | ismailova@unfpa.org |
| UNFPA Office address: | 3, UN 50th Anniversary Street. AZ1001, Baku, Azerbaijan |

Please note the following guidelines for electronic submissions:

- The following reference must be indicated on the envelope or in the email subject line:

RFQ Nº UNFPA/AZE/RFQ/23/014 – Advocacy campaign dedicated to International Father’s Day. Proposals that do not contain the correct email subject line may be overlooked by the procurement officer and therefore not considered.

- The total e-mail size shall not exceed 20 MB (including e-mail body, encoded attachments and headers). Where the technical details are in large electronic files, it is recommended that these be sent separately before the deadline.

- Overview of Evaluation Process

Quotations will be evaluated based on the technical proposal and the total cost of the services (price quote).

The evaluation will be carried out in a two-step process by an ad-hoc evaluation panel. Technical proposals will be evaluated for technical compliance prior to the comparison of price quotes.

- Award Criteria

UNFPA shall award a Purchase Order / Professional Service Contract to the lowest-priced most technically acceptable offer.

- Right to Vary Requirements at Time of Award

UNFPA reserves the right at the time of award of contract to increase or decrease by up to 20% the volume of services specified in this RFQ without any change in unit prices or other terms and conditions.

- Payment Terms

UNFPA payment terms are net 30 days upon receipt of invoice and delivery/acceptance of the milestone deliverables linked to payment as specified in the contract.

- Fraud and Corruption

UNFPA is committed to preventing, identifying, and addressing all acts of fraud against UNFPA, as well as against third parties involved in UNFPA activities. UNFPA’s Policy regarding fraud and corruption is available here:  Fraud Policy. Submission of a proposal implies that the Bidder is aware of this policy.

Suppliers, their subsidiaries, agents, intermediaries and principals must cooperate with the Office of Audit and Investigation Services of UNFPA as well as with any other oversight entity authorized by the Executive Director of UNFPA and with the UNFPA Ethics Advisor as and when required. Such cooperation shall include, but not be limited to, the following: access to all employees, representatives, agents and assignees of the vendor; as well as production of all documents requested, including financial records. Failure to fully cooperate with investigations will be considered sufficient grounds to allow UNFPA to repudiate and terminate the contract, and to debar and remove the supplier from UNFPA’s list of registered suppliers.

A confidential Anti-Fraud Hotline is available to any Bidder to report suspicious fraudulent activities at UNFPA Investigation Hotline.

- Zero Tolerance

UNFPA has adopted a zero-tolerance policy on gifts and hospitality. Suppliers are therefore requested not to send gifts or offer hospitality to UNFPA personnel. Further details on this policy are available here: Zero Tolerance Policy.

- RFQ Protest

Bidder(s) perceiving that they have been unjustly treated in connection with the solicitation or award of a contract may submit a complaint directly to the Chief, Procurement Services Branch at procurement@unfpa.org.

Bidder(s) perceiving that they have been unjustly or unfairly treated in connection with a solicitation, evaluation, or award of a contract may submit a complaint to the UNFPA Head of the Business Unit, Dr. Farid Babayev, UNFPA Assistant Representative at babayev@unfpa.org. Should the supplier be unsatisfied with the reply provided by the UNFPA Head of the Business Unit, the supplier may contact the Chief, Procurement Services Branch at procurement@unfpa.org.

- Disclaimer

Should any of the links in this RFQ document be unavailable or inaccessible for any reason, bidders can contact the Procurement Officer in charge of the procurement to request for them to share a PDF version of such document(s).

PRICE Quotation Form

| Name of Bidder: |  |
| --- | --- |
| Date of the quotation: | Click here to enter a date. |
| Request for quotation Nº: | UNFPA/AZE/RFQ/23/014 |
| Currency of quotation: | AZN |
| Validity of quotation: (The quotation shall be valid for a period of at least 3 months after the submission deadline.) |  |

- Quoted rates must be exclusive of all taxes, since UNFPA is exempt from taxes.

Example Price Schedule below:

| Item | Description |  |
| --- | --- | --- |
| Professional fees |  |  |
| 1. |  |  |
| 2. |  |  |
| 3. |  |  |
| Total Contract Price |  | AZN |

Vendor’s Comments:

I hereby certify that the company mentioned above, which I am duly authorized to sign for, has reviewed RFQ Nº UNFPA/AZE/RFQ/23/014 including all annexes, amendments to the RFQ document (if applicable) and the responses provided by UNFPA on clarification questions from the prospective service providers. Further, the company accepts the General Conditions of Contract for UNFPA and we will abide by this quotation until it expires.

|  | Click here to enter a date. |  |
| --- | --- | --- |
| Name and title | Date and place |  |

ANNEX I:

General Conditions of Contracts:

De Minimis Contracts

This Request for Quotation is subject to UNFPA’s General Conditions of Contract: De Minimis Contracts, which are available in: English, Spanish and French